## Sheet1
S.no | Enhancement Description | Additional Info | Priority | Status | Remarks
1 | Create a scenario for Cylclos payments in BDD Framework | Script for Mobile and Desktop | 1 | Completed
2 | Capture Payments scenario script execution as video. |  | 1 | Completed
3 | Refactor logger in framework. | Now We have debug level logger alone and there is no logger in action files We need to include logger in all level(Debug, Info, Warning, Error and Fatal) | 2 | Completed | Logger refactoring for debug is completed , further fine tuning can be done as per requirements
4 | Reducing Screen shot | Now the framework take screenshot before and after click/Touch operation. In Mobile we often use touch operation, Hence it takes more number of screenshot. We can have option to switch off from config | 3 | Completed | Configuration Included to take screenshot for assertion scenario Alone
5 | Prepare demo script for Native application using BDD framework for Android Application. |  | 4 | Completed
6 | Prepare demo script for Native application using BDD framework for Ios Application. |  | 4
7 | Reading Test Data based on the feature file. |  | 4 |  | Integrating with external data sources for test data
8 | Refactor Common Step definition | Remove duplicate step definitions, optimize the description more relate to the action | 5
9 | Refactor Properties file description | Add relative information in property file and validate the property key is understandable. | 6
10 | Release file lock if it is locked more then 2 min. | Now if the user terminates the 'Test script execution', The lock file will not cleared. Hence it will not allow other script to edit the report file. | 7
11 | Create document for configuring BDD Framework and add new project. |  | 9
12 | Multi browser parallel execution in desktop. |  | 10 | Completed | multiple browser can run in single desktop (1 Chrome, 1 Firefox, 1 IE)
13 | Add java document code in Basic Action interface. | This would helpful while selecting the keyword. | 11 |  | Technical user manual for Method/function/library
14 | Add Allure report in framework | Allure Report added and committed in develop branch | 5 | Completed by Vinoth | Integrate other reports dashboards other than extent report e.g. Allure (Each time we need to generate the report manually)
15 | Isolate Action package(Keywords) as a separate Project. | By this same set of keywords will be used by allover organization. | 8
16 | Uploading to common repository (Git) for usage across projects |  |  |  | Uploading to common repository (Git) for usage across projects
17 | Extend BDD framework for Mainframe (Jagacy), Windows (LeanFT) & API (TBD)
18 | Detailed User manual covering tool installation, fw setup, usage (addition, maintenance, deletion), reporting..etc. with detailed screen shots for each of the above topics
19 | Avoid Retry for undefined/Pending step scenario | If a step is undefined/Pending (not implemented) then no need to retry that scenario
20 | Include Winium in Framework. | To Automate Windows based application |  |  | It was not up to date it was modifies at 2016 and it only has 5 contributors.
21 | convert printStackTrace() as exception. | printStackTrace() will not throw exception hence it we have to analyze the code and made it as exception.
22 | Give reasonable name for methods in common StepDefinition. | These method names are displayed in html report, Hence it is good to have the proper name in stepdefinition.
23 | Screen shot is not attached in html report on failure. |  |  | Completed
23 | Implement GIT SubModule for Action Interfaces & tool Utilities
24 | Implement Maven Test Runner | Maven TestRunner implemented have to analyse why the changes are not working in another machines |  | Completed by Vinoth | Maven TestRunner Developed machine it is working fine
25 | Mobile Execution - how to handle when device details are not entered in device.csv
26 | Run Android scripts in Genymotions emulator
27 | Trigger mobile scripts from Axure Devops? | Getting system not authorized error
28 | Run multiple applications from Maven Test Runner
29 | Invoke Java Class from Mvn Runner | mvn exec
30 | Run the scripts from external JAR file
31 | Error handling when the scenarios given in Excel or not available in the feature file | When not handled , infinite loop is triggered
32 | Page object handling for Both web and Mobile in separate packages?
33 | Multiple Test data Parsing
34 | Scenario wise data mapping
35 | Refactoring the packages and folders into resources
36 | Propery file refactoring - > maintaining every thing from single prop file
37 | Device specification in a single file
38 | Output and results folder clustering
39 | Segregating actions into separate packages
40 | Integrating Auto-Q element based technique?
41 | Framwork Components?
42 | AssignTestSuite ID for Current JVM - Usage?
43 | Page objects scraping and file creation
44 | Clean up Sonar Server properties
45 | cucumber profiles in java
46 | From TestRunner - Trigger SQS Driver , parsing tags or some custom tags and extract the SQSDriver as an separate module

## Sheet2
Features of Framework Scripts writen in Basic language(Gerkin) Parallel Execution. Retry Failed scenarios once. Execution status in Excel Detailed Logger for technical user.